## Dashboard
Test Run & Environment Summary
| PARAMETER | ENVIRONMENT VALUE
| Application Name | TRIPPLE DOUBLE
| App Version | v1.0.27+16.patch1
| Target Platform | Android (OS 15)
| Lead Tester | Palash Jaiswal
| Test Execution Date | September 2026

## Bug report
Bug/Defect Report
|  |  | Application name : |  | TRIPPLE DOUBLE
|  |  | Version : |  | v1.0.27+16.patch1
|  |  | Platform : |  | Android
|  |  | OS Version |  | 15
|  |  | Tester |  | Palash Jaiswal
Bug ID | Bug Title | Precondition | Steps to reproduce | Expected result | Actual result | Severity | Priority | Attachments
Bug001 | Email accepts very long input | none | 1] Open app 2] click on get.set.go 3] enter email with more than 50 characters | restriction of input after a fixed number of characters | the input allows any number of characters entered | Medium | P2 | bug001.video
Bug002 | No screen touch response in Moments tab below the profile photo of the poster | 1] registered through email and logged in 2] open app 3] tap/go to moments tab | touch the screen area below the profile photo of the poster and above the name of the poster | 1] single touch should stop the video from playing and vice-versa 2] double clicking should like or unlike the video | no touch response | High | P1 | bug002.video
Bug003 | Background playing of video | 1] registered through email and logged in 2] open app 3] tap/go to moments tab | while the video is playing and sound is on, tap on "my moments" or "+"(add moments) | the already playing video in moments tab stops | the video and audio does not stop and keeps playing in the background while we are on the my moments/add moments page | Medium | P2 | bug003.video
Bug004 | double tapping to like response error | 1] registered through email and logged in 2] open app 3] tap/go to moments tab | 1] double tap to like the video 2] double tap again to unlike the video and rapidly double tap again to like the video | the video is liked again | a heart appears on the screen showing that the video is liked but the like is not reflected in the like counter | Medium | P3 | bug004.video
Bug005 | improper display of video in moments tab | 1] registered through email and logged in 2] open app 3] tap/go to moments tab | scroll through the section | all videos should be displayed properly | improper/pixelated display of videos | High | P1 | bug005.video
Bug006 | redirection error after uploading a video in moments | 1] registered through email and logged in 2] open app 3] tap/go to moments tab | 1] click on "+" icon 2] select and upload a video 3] click "back arrow" to go to moments main page 4] click on my moments 5] clcik on "+" icon 6] upload another video 7] after getting redirected to the "my moments" page, click on the "back arrow" to go back to "moments" main page | user redirected to "moments" main page | user is redirected to "my moments" again | High | P4 | bug006.video
Bug007 | tapping share button multiple times opens share panel multiple times | 1] registered through email and logged in 2] open app 3] tap/go to moments tab | click on share button rapidly multiple times | share panel opens once | share panel opens as many times as the number of clicks/touches | Low | P4 | bug007.video
Bug008 | touching outside the panel while editing caption exits the whole function | 1] registered through email and logged in 2] open app 3] tap/go to moments tab | 1] click on "+" icon 2] select and upload a video 3] on "my moments"screen, tap on the video under review 4] click on "edit" icon 5] after opening of the edit caption function and the keyboard, click outside the edit caption box and the keyboard | only the keyboard of the phone closes | keyboard and also the edit caption function closes | Low | P4 | bug008,video
Bug009 | profile picture upload error | 1] registered through email and logged in 2] open app 3] tap/go to "Me" tab | 1] click on "edit" button in "My Profile" section 2] tap on profile photo 3] after the phone gallery opens, upload any photo 4] after the photo uploads, click on the "cancel button" | profile photo should not be uploaded | selected photo is uploaded as profile photo | High | P1 | bug009.video
Bug010 | no resuming of video in "moments" tab | 1] registered through email and logged in 2] open app 3] tap/go to moments tab | 1] while the video is playing, switch to any other tab 2] switch back to "moments" tab | the video should resume/restart OR the video should stop with the stopped sign on the video | 1]the video is stopped without the stopped sign displaying 2]when tapped, the stop sign is displayed on the video indicating the video is stopped 3]after tapping again, the video resumes to play | High | P1 | bug010.video
Def001 | grammatical mistake on OTP page | none | 1] Open app 2] click on get.set.go 3] enter valid email address | Instruction line to enter code - Enter the six digit code we "sent" you on mail | Instruction line to enter code - Enter the six digit code we "send" you on mail | Low | P4 | #VALUE!
Def002 | two cancel buttons | 1] registered through email and logged in 2] open app 3] tap/go to moments tab | 1] click follow button infront of the name of the video poster 2] after it shows "following", click the the "following" button | A panel asking confirmation to unfollow with two buttons - Unfollow and Cancel appears | A panel asking confirmation to unfollow with two buttons - Unfollow and Cancel appears along with a "cross sign" on the top right of the panel | Low | P4 | #VALUE!

## RTM
Requirement Traceability Matrix - Defect Mapping
REQ ID | MODULE | REQUIREMENT DESCRIPTION | LINKED TC | BUG/DEF ID | DEFECT SUMMARY | TRACEABILITY STATUS
REQ-AUTH-001 | Authentication | System shall restrict email field length to 50 characters | TC-AUTH-12 | Bug001 | Email accepts very long input without limit | Defect Pending Fix
REQ-MOM-002 | Moments Feed | Full video touch overlay shall support tap-to-pause and double-tap to like | TC-MOM-05 | Bug002 | No touch response below poster photo area | Defect Pending Fix
REQ-MOM-005 | Moments Audio | Navigating away from moments feed shall pause video playback | TC-MOM-18 | Bug003 | Background video audio continues on tab switch | Fix In Progress
REQ-MOM-008 | Social Likes | Double tap to like shall increment backend like counter synchronously | TC-MOM-22 | Bug004 | Double tap animation plays but like count fails to update | Defect Pending Fix
REQ-MOM-010 | Video Quality | Video stream player shall maintain crisp HD rendering aspect ratio | TC-MOM-02 | Bug005 | Improper / pixelated video display | Defect Pending Fix
REQ-NAV-004 | Navigation | Post-upload back button shall navigate strictly to parent feed | TC-NAV-09 | Bug006 | Back button causes navigation loop to My Moments | Defect Pending Fix
REQ-UI-012 | Share Drawer | Share button click event shall be debounced to prevent duplicate drawers | TC-UI-30 | Bug007 | Rapid share clicks open multiple stacked panels | Verified & Resolved
REQ-MOM-015 | Content Editing | Tapping outside dialog shall close soft keyboard only | TC-MOM-33 | Bug008 | Outside touch dismisses edit caption modal entirely | Defect Pending Fix
REQ-PROF-003 | User Profile | Pressing Cancel on profile image edit shall revert uncommitted changes | TC-PROF-07 | Bug009 | Cancel button still saves uploaded profile photo | Fix In Progress
REQ-MOM-020 | Lifecycle State | Switching back to moments tab shall restore video playback state correctly | TC-MOM-41 | Bug010 | Video stays frozen without pause icon after tab return | Defect Pending Fix
REQ-AUTH-005 | OTP Service | OTP screen copy text shall be grammatically correct | TC-AUTH-03 | Def001 | Typo 'send' instead of 'sent' in OTP instructions | Verified & Resolved
REQ-UI-008 | UI Guidelines | Confirmation modal shall use standardized single dismiss control pattern | TC-UI-14 | Def002 | Duplicate cancel options (Cancel button + top X icon) | Verified & Closed